## Requirements
RequirementID | Short Description | Requirement Status (Complete/Incomplete) | Developers Assigned | Developers Who Completed | Standalone/Dependent | Priority | Critical/Not Critical
1 | Create Recipe | Complete | Trevor | Trevor | Standalone | 10 | Critical
2 | Edit Recipe | Complete | Trevor | Trevor | Dependent | 10 | Critical
3 | Delete Recipe | Complete | Trevor | Trevor | Dependent | 10 | Critical
4 | Display Recipe | Complete | Trevor | Trevor | Dependent | 10 | Critical
5 | Scale Recipe |  | Trevor |  | Dependent | 8 | Not Critical
6 | Recipe Ratings |  | Trevor |  | Dependent | 4 | Not Critical
7 | Display Ratings |  | Trevor |  | Dependent | 4 | Not Critical
8 | Allergen Warnings | Complete | Trevor | Trevor | Dependent | 8 | Not Critical
9 | Compare Pantry and Recipe Ingredients |  | Trevor |  | Dependent | 2 | Not Critical
10 | Create Shopping Cart | Complete | Joseph | Joseph | Standalone | 10 | Critical
11 | Edit Shopping Cart | Complete | Joseph | Joseph | Dependent | 10 | Critical
12 | Delete Shopping Cart | Complete | Joseph | Joseph | Dependent | 10 | Critical
13 | Display Shopping Carts | Complete | Joseph | Joseph | Dependent | 10 | Critical
14 | Sign Up as a New User | Complete | Joseph | Joseph | Standalone | 10 | Critical
15 | Login as an Existing User | Complete | Joseph | Joseph | Dependent | 10 | Critical
16 | Display Recipes&Carts on Profile Page | Complete | Joseph | Joseph | Dependent | 7 | Not Critical
17 | Persistent Data between Logins | Complete | Joseph | Joseph | Dependent | 10 | Critical

## Testing
TestID | TestDescription | Test Status (Pass/Fail) | Testers Assigned | Testers Who Completed | RequirementID | Requirement Status (Complete/Incomplete) | Developers Assigned | Developers Who Completed